## Sheet1
Sl. No. | Group No. | Project Name | Name | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
2 | 3 | Cric24 Application | Shagufta Naz | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
20 | 3 | Cric24 Application | Neha Bhargava | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
15 | 3 | Cric24 Application | Pranav Joshi | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
11 | 3 | Cric24 Application | Arvish Saluja | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
17 | 3 | Cric24 Application | Anirban Deb | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
16 | 3 | Cric24 Application | Akash Sarkar | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
19 | 3 | Cric24 Application | Swaroop Nath | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment